## Team Members
Enter the First Name of Each Team Member
Abdulrhman almuhanna
Hatem AlHarbi
Ali Alkhalifah
Abdullah Alwehaibi
Motaz Alghamdey

## Product Backlog
Sprint Number | User Story ID | User Story Title | Brief Description | Additional Information | Priority | Status
| S |  | As a [role], I want [some goal] so that [some reason]. |  | 3-low | To Do
| S1 | Interface | As a User, I want to smoothly progress through different educational levels so that I can access content that matches my current learning proficiency. |  | 2-medium | To Do
| S2 | Awards | As a Student, I want to earn and collect educational awards so that I can feel a sense of accomplishment and motivation to continue learning. |  | 3-low | To Do
| S3 | Levels | As a Student, I want to progress through different educational levels so that I can experience a gradual and challenging learning journey. |  | 1-high | To Do
| S4 | Audio And soundeffect | As an Student, I want to integrate engaging audio and sound effects into the game to enhance the learning experience for users, fostering a more immersive and enjoyable educational environment. |  | 2-medium | To Do
| S5 | Score system | As a Student, I want a robust scoring system so that I can track my progress, receive feedback on my performance, and stay motivated to improve my educational achievements. |  | 2-medium | To Do
| S6 | Setting menu | As a Student, I want access to settings menu so that I can personalize my learning experience and adjust game preferences according to my individual needs. |  | 2-medium | To Do
| S7 | Asset creation | As a Developer, I want to create visually engaging and informative assets for the game so that I can enhance the overall educational experience by presenting information in a visually appealing and comprehensible manner. |  | 2-medium | To Do
| S8 | Educational focus | As an Developer, I want to prioritize and align game content with educational objectives so that I can ensure a meaningful and effective learning experience for users. |  | 1-high | To Do
| S9 | difficulty | As a Student, I want the ability to adjust the difficulty level of the game so that I can tailor the challenge to match my current skill level, promoting a personalized and adaptive learning experience. |  | 2-medium | To Do
| S10 | IOS/Android | As a Developer, I want to optimize the app's performance for both iOS and Android platforms so that I can ensure a seamless and consistent educational experience for users across different devices. |  | 1-high | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 1-high | To Do
[5 empty] | 2-medium | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do

## Sprint Template (Make a copy!)
User Story ID | Task | Expected Hours | Actual Hours | Person | Status | Date Completed | [6 empty] | Chart Dates | Completed Hours On Date | Current Completed Work | Current Remaining Work | Ideal Remaining Work
S1 | Brief description |  |  |  | To Do |  | Sprint Number: | 0 | Person | Hours Assigned | Hours Completed | Percentage Complete | 2019-03-30 | 0 | 0 | 0 | 0
[5 empty] | To Do |  | Start Date: | 2019-03-30 | Abdulrhman almuhanna | 0 | 0 | 0% | 2019-03-31 | 0 | 0 | 0 | 0
[5 empty] | To Do |  | Sprint Length | 14 | Hatem AlHarbi | 0 | 0 | 0% | 2019-04-01 | 0 | 0 | 0 | 0
[5 empty] | To Do |  | Hours Per Day: | 0 | Ali Alkhalifah | 0 | 0 | 0% | 2019-04-02 | 0 | 0 | 0 | 0
[5 empty] | To Do |  |  |  | Abdullah Alwehaibi | 0 | 0 | 0% | 2019-04-03 | 0 | 0 | 0 | 0
[5 empty] | To Do |  |  |  | #REF! | 0 | 0 | 0% | 2019-04-04 | 0 | 0 | 0 | 0
[5 empty] | To Do |  |  |  | Motaz Alghamdey | 0 | 0 | 0% | 2019-04-05 | 0 | 0 | 0 | 0
[5 empty] | To Do | [7 empty] | 2019-04-06 | 0 | 0 | 0 | 0
[5 empty] | To Do |  |  |  | Total: | 0 | 0 | 0% | 2019-04-07 | 0 | 0 | 0 | 0
[5 empty] | To Do | [7 empty] | 2019-04-08 | 0 | 0 | 0 | 0
[5 empty] | To Do | [7 empty] | 2019-04-09 | 0 | 0 | 0 | 0
[5 empty] | To Do | [7 empty] | 2019-04-10 | 0 | 0 | 0 | 0
[5 empty] | To Do | [7 empty] | 2019-04-11 | 0 | 0 | 0 | 0
[5 empty] | To Do | [7 empty] | 2019-04-12 | 0 | 0 | 0 | 0
[5 empty] | To Do | [7 empty] | 2019-04-13 | 0 | 0 | 0 | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
Formulas:
Chart Dates = IF(AND(ISDATE([Chart Dates, row above]),[Chart Dates, row above]-J3<J4), [Chart Dates, row above]+1, "")
Current Remaining Work = IF([Chart Dates] <= TODAY(), M10-[Current Completed Work], "")

## Sprint 1
User Story ID | Task | Expected Hours | Actual Hours | Person | Status | Date Completed | [6 empty] | Chart Dates | Completed Hours On Date | Current Completed Work | Current Remaining Work | Ideal Remaining Work
S10 | Learn developing using flatter | 3 | 3 | Abdulrhman almuhanna | Done | 2023-01-04 | Sprint Number: | 1 | Person | Hours Assigned | Hours Completed | Percentage Complete | 2022-12-30 | 0 | 0 | 12 | 12
S1 | Making an interface | 3 | 4 | Abdulrhman almuhanna | Done | 2023-01-05 | Start Date: | 2023-12-31 | Abdulrhman almuhanna | 6 | 6 | 100% | 2022-12-31 | 0 | 0 | 12 | 10.8
| Design a logo | 2 | 1 | Hatem AlHarbi | Done | 2023-01-01 | Sprint Length | 10 | Hatem AlHarbi | 2 | 2 | 100% | 2023-01-01 | 2 | 2 | 10 | 9.6
| Upload the code to gethub | 1 | 1 | Ali Alkhalifah | Done | 2023-01-05 | Hours Per Day: | 1.2 | Ali Alkhalifah | 1 | 1 | 100% | 2023-01-02 | 0 | 2 | 10 | 8.4
| Learn andriod Studio | 2 | 1 | Abdullah Alwehaibi | Done | 2023-01-03 |  |  | Abdullah Alwehaibi | 2 | 2 | 100% | 2023-01-03 | 2 | 4 | 8 | 7.2
| Update user stories in the backlog | 1 | 1 | Motaz Alghamdey | Done | 2023-01-05 |  |  | #REF! | 0 | 0 | 0% | 2023-01-04 | 3 | 7 | 5 | 6
[5 empty] | To Do |  |  |  | Motaz Alghamdey | 1 | 1 | 100% | 2023-01-05 | 5 | 12 | 0 | 4.8
[5 empty] | To Do | [7 empty] | 2023-01-06 | 0 | 12 | 0 | 3.6
[5 empty] | To Do |  |  |  | Total: | 12 | 12 | 100% | 2023-01-07 | 0 | 12 | 0 | 2.4
[5 empty] | To Do | [7 empty] | 2023-01-08 | 0 | 12 | 0 | 1.2
[5 empty] | To Do | [7 empty] | 2023-01-09 | 0 | 12 | 0 | 0
[5 empty] | To Do | [7 empty] | 2023-01-10 | 0 | 12 | 0 | 0
[5 empty] | To Do | [7 empty] | 2023-01-11 | 0 | 12 | 0 | 0
[5 empty] | To Do | [7 empty] | 2023-01-12 | 0 | 12 | 0 | 0
[5 empty] | To Do | [7 empty] | 2023-01-13 | 0 | 12 | 0 | 0
[5 empty] | To Do | [7 empty] | 2023-01-14 | 0 | 12 | 0 | 0
[5 empty] | To Do | [7 empty] | 2023-01-15 | 0 | 12 | 0 | 0
[5 empty] | To Do | [7 empty] | 2023-01-16 | 0 | 10 | 2 | 0
[5 empty] | To Do | [7 empty] | 2023-01-17 | 0 | 10 | 2 | 0
[5 empty] | To Do | [7 empty] | 2023-01-18 | 0 | 8 | 4 | 0
[5 empty] | To Do | [7 empty] | 2023-01-19 | 0 | 5 | 7 | 0
[5 empty] | To Do | [7 empty] | 2023-01-20 | 0 | 0 | 12 | 0
[5 empty] | To Do | [7 empty] | 2023-01-21 | 0 | 0 | 12 | 0
[5 empty] | To Do | [7 empty] | 2023-01-22 | 0 | 0 | 12 | 0
[5 empty] | To Do | [7 empty] | 2023-01-23 | 0 | 0 | 12 | 0
[5 empty] | To Do | [7 empty] | 2023-01-24 | 0 | 0 | 12 | 0
[5 empty] | To Do | [7 empty] | 2023-01-25 | 0 | 0 | 12 | 0
[5 empty] | To Do | [7 empty] | 2023-01-26 | 0 | 0 | 12 | 0
[5 empty] | To Do | [7 empty] | 2023-01-27 | 0 | 0 | 12 | 0
[5 empty] | To Do | [7 empty] | 2023-01-28 | 0 | 0 | 12 | 0
[5 empty] | To Do | [7 empty] | 2023-01-29 | 0 | 0 | 12 | 0
[5 empty] | To Do | [7 empty] | 2023-01-30 | 0 | 0 | 12 | 0
[5 empty] | To Do | [7 empty] | 2023-01-31 | 0 | 0 | 12 | 0
[5 empty] | To Do | [7 empty] | 2023-02-01 | 0 | 0 | 12 | 0
[5 empty] | To Do | [7 empty] | 2023-02-02 | 0 | 0 | 12 | 0
[5 empty] | To Do | [7 empty] | 2023-02-03 | 0 | 0 | 12 | 0
[5 empty] | To Do | [7 empty] | 2023-02-04 | 0 | 0 | 12 | 0
[5 empty] | To Do | [7 empty] | 2023-02-05 | 0 | 0 | 12 | 0
[5 empty] | To Do | [7 empty] | 2023-02-06 | 0 | 0 | 12 | 0
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
Formulas:
Current Remaining Work = IF([Chart Dates] <= TODAY(), M10-[Current Completed Work], "")
Chart Dates = IF(AND(ISDATE([Chart Dates, row above]),[Chart Dates, row above]-J3<J4), [Chart Dates, row above]+1, "")